## Slide 1
OPOF Monitoring Biodiversity -
Progress Report
6th February 2019
Sarah Jackson, Senior Ecologist

## Slide 2
What is the ‘Monitoring Biodiversity’ project
Monitoring four of the delivery projects over 4 years.
Surveys of a selection of sites in each project
Monitoring visits to compare to baseline to see effects of management on biodiversity of the site

## Slide 3
A range of surveys chosen for each site based on the habitats present, species it is likely to support and nature of works:
  Butterflies
  Bumblebees
  Birds
  Bats
  Odonata (dragonflies and damselflies)
  Reptiles
  Botanical surveys - hedgerow and woodland condition assessment
Surveys are undertaken by the Trust; professional, skilled and trained volunteers; and University of Southampton students and placements.

## Slide 4
Repeat of all sites surveyed to date
Between 2 and 4 years of data for analysis
Final Year
 | Year 1 | Year 2 | Year 3 | Year 4 | Target Total No. of Sites
BB | 6 | 8 | 8 | 8 | 7
NSS | 9 | 13 | 11 | 11 | 18
WW | 8 | 15 | 20 | 20 | 16
NFNNS | 10 | 10 | 10 | 10 | 10

## Slide 5
Volunteers
New & returning surveyors – 28 returning volunteers
Volunteer days = 173 days to date
Provided bird, bumblebee and butterfly training days for volunteers
Two sites included in University of Southampton 2nd year course – Warren Copse & Avon Tyrrell
Two university placements

## Slide 6
Master spreadsheet containing all survey results
Visual representation
- using GIS – bird, bat, rhododendron
- Fixed Point Photography (FPP)
Comparison by site of baseline with final year of monitoring
Picking out highlights at species and habitat level
- indicator species e.g. barbastelle
- number and diversity of species
What are we doing with the data?

## Slide 7
Challenges
Finding landowners / sites
Retaining sites for duration of project – changes in landowner, not following MoU
- Not reached target number of sites for Natures Stepping Stones, but have for other projects
Data collection – very short window to demonstrate success, particularly in woodlands

## Slide 8
Signs of Success
Newly planted hedgerow in BB was used for the first time in 2017 by common pipistrelle bat
2016
2017

## Slide 9
Works to restore hedgerows are having a positive effect on bird numbers and species
Chart: Year
Number | 31 | 44 | 49
Species | 14 | 23 | 25

## Slide 10
Battling Rhododendron - an average reduction of 83%, with one site having removed 98%
Butterfly Records
Chart: Year
Number | 11 | 28 | 34
Species | 5 | 9 | 16

## Slide 11
Increased bat activity following works on WW site

## Slide 12
Butterflies are also benefitting from scrub and tree management works on a meadow and copse owned by one landowner
Chart: Year
Number | 22 | 53 | 79
Species | 8 | 8 | 14

## Slide 13
And birds on another site in both NSS & WW
Chart: Year
Number | 63 | 85 | 84
Species | 19 | 21 | 21
Goldfinch on Twig by Darin Smith

## Slide 14
Records
6959 new records for 208 species
Arranging data sharing agreement with landowners so these can be shared with Hampshire Biodiversity Information Centre / County Recorders

## Slide 15
Any Questions?